## Product Backlog
EPIC ID | EPIC Name | User Story ID | User Story | Acceptance criteria | Estimate (User Story Points) | Comments
EPIC 1 | User Authentication & Profile Management | US1-1 | As a student or staff, I want to log in/log out using CUNET SSO So that I can securely access the system with my university credentials. | Given the user is on the login page When the user clicks "Log in with ChulaEmail" and authenticates successfully Then the system maps their university role (Student or Staff), creates an active session, and redirects them to the main dashboard. | 8 | FR-1.1
Given the user is attempting to log in via ChulaEmail When the ChulaEmail returns an invalid credential or unauthorized status Then the system denies access and displays the error message: "Invalid ChulaEmail credentials. Please try again.
Given the user is currently logged into the system When the user clicks the "Log out" button Then the system terminates their active session, clears all authentication tokens, and redirects them to the login page.
|  | US1-2 | As an external visitor, I want to register and log in with personal details So that I can have an account to purchase passes and use library facilities. | Given an external visitor is on the registration form When they submit the form with all required fields (Full Name, valid Citizen ID/Passport format, Phone, valid Email) Then the system creates the account and displays a "Registration Successful" confirmation message. | 5 | FR-1.2
Given a visitor enters an Email and Citizen ID that already exists in the database When they click submit Then the system highlights that duplicated field and displays: "An account with this [Email/ID] already exists."
Given a visitor leaves mandatory fields blank or uses an invalid email format When they attempt to submit the form Then the system prevents submission and highlights the specific fields in red with appropriate helper text; empty fields show "This field is required."; fields with an invalid format show "Please enter a valid [field name]."
|  | US1-3 | As a librarian (admin), I want to log in with dedicated administrative privileges So that I can manage library operations, seats, and reports. | Given the librarian is on the admin login interface, When entering valid username and password matching a record where role = "Admin", Then the system grants access to the administrative dashboard and privileged features. | 3 | FR-1.3
Given the librarian enters an incorrect username or password, When attempting to log in via the admin login interface, Then system displays "Incorrect username or password." and denies access.
Given a non-admin user (student, staff, or visitor) attempts to log in through the admin login interface, When the credentials are submitted, Then the system denies administrative access, even if the credentials are valid for a regular account.
|  | US1-4 | As a user, I want to edit my personal contact information So that my account details remain up to date. | Given a ChulaEmail user (Student/Staff) is on their profile settings page When the page loads Then their Name, Student/Staff ID, and ChulaEmail are displayed as read-only, and only their Contact Phone Number, Password can be edited. | 2 | FR-1.4
Given an External Visitor is on their profile settings page When they attempt to edit their Name, Phone Number, or Email, Password Then the system validates the new input and updates the database, but leaves their Citizen ID/Passport field locked.
|  | US1-5 | As a user, I want to view my profile, behavior credit score, and score history So that can monitor my reservation standing and penalty logs. | Given the user is on the profile screen, When viewing account details, Then the system displays the current behavior score and a chronological log of score changes. | 2 | FR-1.5
Given a new user who has no penalty or score-change history, When viewing the profile screen, Then the system displays the default full behavior score with an empty score-history log (not an error).
Given the user has one or more past score deductions or admin adjustments, When viewing the score history, Then each entry displays the date, reason, and the amount of score change.
EPIC 2 | Seat Searching & Browsing | US2-1 | As a user, I want to view the interactive library layout and zone maps So that I can understand the physical arrangement and explore different study areas of the library. | Given the user is on the seat searching page, When the library layout is loaded, Then the system should display the 2D floor plan clearly showing all distinct zones (Silent, Group, Common) and table positions and facility(Power Plug). | 5 | FR-2.1
Given the user interacts with the floor map (pan/zoom/select zone), When switching between different areas or floors, Then the system should smoothly render the corresponding zone layout without UI clipping or lag.
Given the layout data fails to load due to network or server issues, When the user attempts to view the map, Then the system should display an appropriate error message and provide a retry button.
|  | US2-2 | As a user, I want to see the real-time status of each table on the map So that I know immediately which seats are currently available, booked, in-use, or closed. | Given the user is viewing the table map, When viewing individual tables, Then the system should indicate each table's status with distinct visual indicators/colors: "Available", "Reserved", "Occupied", and "Closed". | 8 | FR-2.2
Given another user makes a booking, checks in, or releases a table, When the table status changes on the server, Then the system should update the table status on the user's screen in real-time without requiring a full manual page refresh.
Given a table is marked as "Closed" (maintenance or library policy), When the user selects that table, Then the system should indicate that the seat is temporarily unavailable and prevent booking actions.
|  | US2-3 | As a user, I want to filter tables by zone type and available amenities So that I can quickly find seats that meet my specific study requirements (e.g., power outlets, quiet space). | Given the user is on the seat searching page with active filter controls, When the user applies filters by zone type (Silent, Group, Common) and/or amenities ( amount Power Plug, have Large Screen ) Then the system should highlight/display only tables that match all selected criteria. | 2 | FR-2.3
Given no tables match the applied filter criteria, When the filter query is executed, Then the system should display a friendly notice "No tables match your selected filters" and suggest clearing filters.
Given active filters are applied, When the user clicks "Reset/Clear Filters", Then the system should instantly restore the map to show all tables across all zones.
|  | US2-4 | As a user, I want to check table availability for a specific future date and time slot So that I can plan my library visits and reserve study spaces in advance. | Given the user selects a target date and time range (current hours, specific hours, all-day view), When querying seat availability, Then the system should display the table layout reflecting availability and showing available time slots across that period. | 8 | FR-2.4
Given the user selects a date or time outside valid library operating parameters (e.g., past dates or outside operating hours), When attempting to query availability, Then the system should display an appropriate validation message.
Given a table is partially booked during the selected browsing time window, When viewing the table details, Then the system should clearly illustrate the booked vs. open time intervals on a timetable preview.
EPIC 3 | Table Reservation System | US3-1 | As a user, I want to select a table and specify the start and end time So that I can reserve a workspace according to my schedule. | Given an available table and valid timeslot, When the user submit a booking request within allowed duration, Then enforce 1-booking-per-user policy and confirm the reservation. | 2 | FR-3.1 & FR-3.2 & FR-3.3
Given an available table and a selected timeslot, When the user submits a booking request exceeding the maximum duration or outside operating hours, Then reject the booking request and display an error message detailing the duration limits.
Given an active overlapping booking exists for the user, When attempting to book another table, Then reject the request and show an error message.
|  | US3-2 | As a user, I want the system to hold/lock the table during confirmation So that double-booking does not occur with another user. | Given a table is being confirmed by User A, When User B attempts to book the same table and timeslot simultaneously, Then lock the table for User A and notify User B that the seat is unavailable. | 3 | FR-3.4
Given User A has locked a table for booking, When User A does not confirm the booking within 5 minutes (Timeout), Then automatically release the lock and restore the table status to "Available".
|  | US3-3 | As a user, I want to view my booking history and active reservation with a check-in trigger on the home screen, So that I can track my bookings and quickly check in at my table. | Given an authenticated user on the booking history page, When fetching reservations, Then display all past, cancelled, and active bookings with timestamps, zones, and seat numbers. | 3 | FR-3.5
Given an authenticated user with an active upcoming reservation, When accessing the home/dashboard screen, Then display the active booking card showing Table Number, Zone, Timeslot, and a "Scan Table QR to Check-in" action button.
EPIC 4 | Check-in & Verification System | US4-1 | As a user, I want to check in on-site at the library So that my reservation becomes active and prevents cancellation. | Given a user has a reservation within the allowed check-in window (starting 15 minutes before the booking start time), When the user checks in on-site within that window, Then the system records the check-in time and updates the seat status to "In-use" | 3 | FR-4.1 & FR-4.2
Given a user attempts to check in before the check-in window opens, When the system compares the current time against the allowed window, Then the system rejects the check-in and informs the user it's too early, showing the time when check-in becomes available
Given a reservation has already been auto-marked as "No-show" after the grace period expired (15 minutes after the booking start time), When the user attempts to check in, Then the system rejects the check-in and informs the user the reservation was cancelled due to No-show
|  | US4-2 | As a system, I want to automatically detect No-shows and release seats So that unutilized tables become available for other users. | Given a reservation has not been checked in within the grace period, When the system detects the grace period has expired, Then the system automatically set the reservation status to "No-show" and release table back to "Available". | 2 | FR-4.3 & FR-4.4
Given a reservation has just been marked as No-show, When the status update completes, Then the system notifies the user that they were marked No-show and that their behavior score will be deducted
EPIC 5 | Cancellation & Penalty Management | US5-1 | As a user, I want to cancel my reservation before the cutoff deadline So that other students can use the seat without penalty to my score. | Given an upcoming reservation, When the user cancels before the allowed cutoff time, Then mark booking as cancelled and release the seat without score deduction. | 1 | FR-5.1
|  | US5-2 | As a system, I want to penalty user's score automatically when "No show" occur So that the behaviour score always up to date | Given the penalty process runs , When a booking status changes to No-show, Then automatically deduct credit score and record a deduction log. | 1 | FR-5.2
|  | US5-3 | As a system, I want to automatically suspend seat reservation privileges for users whose score drops below 50 points So that policy violations are strictly enforced. | Given a user has a valid score of 50 or above (e.g., 80 points), When submitting a booking, Then the system allows the reservation to proceed normally. | 2 | FR-5.3
Given a user has a behavior score below 50 points (e.g., 40 points), When attempting to book a seat, Then the system rejects the request and displays a suspension message.
|  | US5-4 | As a librarian (admin), I want to manually adjust a user's behavior credit score So that system errors or valid appeals can be resolved fairly. | Given the librarian a permission to adjust user behaviour score When there is an appeal Then libralian adjust score to the right value and show the result of changing | 2 | FR-5.4
Given the librarian a permission to adjust user behaviour score When the error occur to the system Then libralian adjust score to the right value and show the result of changing
EPIC 6 | Visitor Ticketing System | US6-1 | As an external visitor, I want to pay for a service ticket online, So that I can access and use the facilities. | Given an external visitor is on the ticket payment page, When completing payment via the payment gateway, Then the system should allow the action and complete the ticket purchase. | 13 | FR-6.1
Given the payment details or inputs are incomplete or invalid, When the visitor attempts to make a payment, Then the system should display an appropriate error message.
|  | US6-2 | As an external visitor, I want to view my ticket details, payment history, and valid time period, So that I can verify my transaction details and know when the ticket can be used. | Given the user is on the ticket history or ticket detail page, When the user views their purchased ticket, Then the system should display complete ticket details, payment history, and the valid time period for usage. | 2 | FR-6.2
|  | US6-3 | As an external visitor, I want my ticket status to automatically update to "Active" immediately after payment, So that I can access the service right away without delay. | Given the user has successfully completed the ticket payment, When the payment confirmation is received, Then the system should update the ticket status to "Active" immediately. | 2 | FR-6.3
Given the payment process is incomplete, pending, or failed, When the system checks for payment completion, Then the system should keep the ticket inactive and display an appropriate error message.
EPIC 7 | Facility & Issue Management | US7-1 | As a user I want to report or provide the detail or the picture about the issue with the equipment, So that maintenance tasks can be tracked and resolved effectively. | Given the user is on the main page, When the user open an issue report function, Then the systems direct the user to the issue reporting form. | 2 | FR-7.1 & FR-7.2
Given the issue reporting form, When submitting issue details, timestamp, and table/zone Id, Then the systems displays a success message and creates an issue ticket
Given the issue reporting form, When submitting without filling in required details (table/zone Id, issue details, timestamp), Then the system displays an error message pointing out the missing fields and does not create an issue ticket.
|  | US7-2 | As an admin, I want to be able to view and filter the status of reported issues So that maintenance tasks can be tracked and resolved effectively. | Given the admin issue management list, When they open the list, Then the system displays all reported issues with their details, timestamps, desk numbers, and current status. | 1 | FR-7.3
Given the admin issue management list, When they filter the list base on issue detail or status(in Progress, Pending, Completed), Then the system update the displayed list based on the filter.
|  | US7-3 | As an admin, I want to be able to update the status of reported issues So that maintenance tasks can be tracked and resolved effectively. | Given the admin issue management list, When they updates issue status (in Progress, Pending, Completed) and notes, Then update the ticket and reflect facility availability changes. | 1 | FR-7.4
83

## Sprint1
[11 empty] | 25 aug | 26 aug | 27 aug | 28 aug | 29 aug | 30 aug | 31 aug | 1 sep | 2 sep | 3 sep | 4 sep | 5 sep | 6 sep | 7 sep | 8 sep | 9 sep | 10 sep | 11 sep | 12 sep | 13 sep | 14 sep
| EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer | Count | Status | Original Estimate | Avg/Person | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Sprint Review
Sprint 1 | EPIC 1 | User Authentication & Profile Management | US1-1 | As a student or staff, I want to log in using CUNET SSO So that I can securely access the system with my university credentials. | Setup Database & User/Role Schema (PostgreSQL + Prisma) | Kaopoon, Andy | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Integrate Chula Email SSO OAuth2/SAML Authentication Flow | Poom, Hill | 2 | To Do | 5 | 2.5 | 25 aug Day 1: 5
[5 empty] | Implement Role Mapping (Student/Staff) & Session/JWT Management | Andy, Punt | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Design & Implement Chula Email Login Landing UI | Kla, Nine | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Logout API & Frontend Session Clearance | Punt, Kaopoon | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
|  |  | US1-2 | As an external visitor, I want to register and log in with personal details So that I can have an account to purchase passes and use library facilities. | Design Visitor Registration & Login UI (Responsive Form) | Tin, Soda | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Visitor Registration API with Email/Citizen ID Duplicate Validation | Hill, Punt | 2 | To Do | 4 | 2 | 25 aug Day 1: 4
[5 empty] | Implement Password Hashing (bcrypt) & Visitor Login API | Poom, Punt | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Client-side Form Validation (Email format, Thai ID/Passport) | Kla, Tin | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
|  |  | US1-3 | As a librarian (admin), I want to log in with dedicated administrative privileges So that I can manage library operations, seats, and reports. | Design Admin Login Page & Error Feedback UI | Soda, Kla | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Admin Role-Based Access Control (RBAC Middleware) | Andy, Hill | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Implement Secure Admin Session Handling (Checking if logging-in account's status is admin) | Poom, Punt | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
|  |  | US1-4 | As a user, I want to edit my personal contact information So that my account details remain up to date. | Design Profile Settings UI (Read-only or Editable fields) | Tin, Nine | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
[5 empty] | Implement Update Profile API & Input Validation | Kaopoon, Punt | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Role-based Field Lock Constraints (Read-only or Editable controls) | Nine, Soda | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
|  |  | US1-5 | As a user, I want to view my profile, behavior credit score, and score history So that can monitor my reservation standing and penalty logs. | Design Profile Score Badge & History Log UI (Handling Default Score & Empty Log State) | Soda, Tin | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement API to Fetch Score | Andy, Hill | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
| EPIC 2 | Seat Searching & Browsing | US2-1 | As a user, I want to view the interactive library layout and zone maps So that I can understand the physical arrangement and explore different study areas of the library. | Design 2D Floor Plan UI Components (Silent, Group, Common Zones) | Kla, Nine | 2 | To Do | 5 | 2.5 | 25 aug Day 1: 5
[5 empty] | Design & Setup Zone/Table Database Models | Kaopoon, Andy | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement API to Fetch Floor Layout & Zone Metadata | Poom, Punt | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Interactive Map Rendering (Pan, Zoom, Zone Switch) on Frontend | Tin, Kla | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Implement Map Loading Error State & Retry UI Button | Nine, Soda | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
|  |  | US2-2 | As a user, I want to see the real-time status of each table on the map So that I know immediately which seats are currently available, booked, in-use, or closed. | Design visual status indicators and color-coding for tables (Available, Booked, In-use, Closed) | Kla, Tin | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
[5 empty] | Implement Backend API endpoint to fetch dynamic table statuses | Kaopoon, Hill | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Set up auto-polling with SWR / TanStack Query on Frontend for real-time status updates | Nine, Soda | 2 | To Do | 5 | 2.5 | 25 aug Day 1: 5
[5 empty] | Implement UI logic to disable interaction and show maintenance notice for "Closed" tables | Tin, Kla | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
|  |  | US2-3 | As a user, I want to filter tables by zone type and available amenities So that I can quickly find seats that meet my specific study requirements (e.g., power outlets, quiet space). | Implement Filter API | Kaopoon, Andy | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Design Filter UI Components (Dropdowns/Toggles for amenities) | Nine, Soda | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
[5 empty] | Integrate Client-side Filter State & API Data Fetching Logic | Kla, Nine | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Filter Empty State UI ("No tables match") & Clear Filters Button | Soda, Tin | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
|  |  | US2-4 | As a user, I want to check table availability for a specific future date and time slot So that I can plan my library visits and reserve study spaces in advance. | Design & build Date and Time Slot Picker UI components | Kla, Soda | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
[5 empty] | Implement Backend API to query table availability for a specified date and time window | Poom, Hill | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Build Timetable Preview UI component to display booked vs. available time intervals | Nine, Tin | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement validation logic for invalid target dates | Andy, Punt | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
| EPIC 3 | Table Reservation System | US3-1 | As a user, I want to select a table and specify the start and end time So that I can reserve a workspace according to my schedule. | Design & build Reservation Modal/Form UI with Start Time and End Time pickers | Kla, Soda | 2 | To Do | 1 | 0.5 | bar: 25 aug Day 1
[5 empty] | Implement Backend validation logic for booking rules (1-booking-per-user policy, max allowed duration, operating hours) | Poom, Andy | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Backend API endpoint to submit booking requests and save reservation records to Database | Poom, Punt | 2 | To Do | 4 | 2 | 25 aug Day 1: 4
[5 empty] | Implement Frontend error handling UI for validation failures (exceeding time limit, user already has an active booking) | Nine, Tin | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
|  |  | US3-2 | As a user, I want the system to hold/lock the table during confirmation So that double-booking does not occur with another user. | Implement temporary table locking mechanism in Backend database/cache during confirmation flow to prevent double-booking | Andy, Punt | 2 | To Do | 4 | 2 | 25 aug Day 1: 4
[5 empty] | Implement automatic lock expiration/release service (5-minute timeout) to revert table status back to "Available" if abandoned | Kaopoon, Hill | 2 | To Do | 3 | 1.5 | 25 aug Day 1: 3
[5 empty] | Implement Frontend notification/alert UI when a user attempts to select a table currently locked by another user | Soda, Kla | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
|  |  | US3-3 | As a user, I want to view my booking history and active reservation with a check-in trigger on the home screen, So that I can track my bookings and quickly check in at my table. | Build Booking History UI page to display logs of all past, cancelled, and active reservations | Tin, Soda | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Implement Backend API endpoints to fetch user's booking history logs and current active booking data | Poom, Andy | 2 | To Do | 2 | 1 | 25 aug Day 1: 2
[5 empty] | Build Active Booking Card component on Dashboard showing table details(table id and amenities), timeslot, and the "Scan Table QR to Check-in" action button | Tin, Kaopoon | 2 | To Do | 4 | 2 | 25 aug Day 1: 4
[9 empty] | Total Hour: 108 | total work left | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Avg Per Person: 12
[5 empty] | Name | Nickname | Tasks Count | Man Hour
[5 empty] | Kla | Kla (FE) | 11 | 11.5
[5 empty] | Poom | Poom (BE) | 8 | 12
[5 empty] | Andy | Andy (BE) | 10 | 12
[5 empty] | Kaopoon | Kaopoon | 8 | 10.5
[5 empty] | Soda | Soda (FE) | 12 | 12
[5 empty] | Hill | Hill (BE) | 7 | 10.5
[5 empty] | Nine | Nine (FE) | 10 | 12.5
[5 empty] | Tin | Tin (FE) | 12 | 12
[5 empty] | Punt | Punt (BE) | 10 | 15